## In-Person Event
Fill in your event name and date in the yellow boxes below and dates for each task will automatically update. This list provides suggested timing -- please modify the tasks and timeline to meet the requirements of your specific event.
Event Name |  | Event Date: | 2021-05-20
|  | Weeks Out | Target Date | Status
Venue/Budget
Draft event budget, objectives, attendence goals; format and panelist options |  | 20 | 2020-12-31
Research venue, and date options |  | 18 | 2021-01-14
Book venue/Confirm event format and date |  | 16 | 2021-01-28
Schedule a meeting with the Marketing Lead at the Community College to go over logistics, dates, times, details, etc.
Work with Development Officers to identify donors that might want to sponsor/participate in event |  | 12
Determine Room-Set Up/Visit site |  | 3 | 2021-04-29
check-in area, podium, head table, audience set-up, lighting, temperature control, etc
Confirm room set-up with Venue |  | 1 | 2021-05-13
Speakers/Panel
Recruit panelists |  | 12 | 2021-02-25
Finalize/confirm all panelists |  | 8 | 2021-03-25
Collect bios |  | 6 | 2021-04-08
Create script/slides for UWBA speakers |  | 3 | 2021-04-29
Draft script for speakers and/or panel questions |  | 3 | 2021-04-29
Recruit CBOs, clients and county officials to act as media spokespersons |  | 3 | 2021-04-29
Provide or collect script/anticipated questions |  | 2 | 2021-05-06
Final instructions to all speakers/panelists |  | 1 | 2021-05-13
Coordinate on-site media interviews with CBOs, clients, and county officials |  | 0 | 2021-05-20
Invitation
Determine invitation format (electronic/printed) and requirements |  | 12 | 2021-02-25
Print Invitation
| Invitation design approved (allow 2 weeks for printing, 1 week for prep) | 9 | 2021-03-18
| Compile mailing lists (print and electronic) | 9 | 2021-03-18
| Invitations printed | 7 | 2021-04-01
| Prep Invitation mailing | 7 | 2021-04-01
| Invitations in the Mail | 6 | 2021-04-08
Electronic Invitation
| Email list compiled | 9 | 2021-03-18
| Draft invitation designed | 8 | 2021-03-25
| Final invitation approved | 7 | 2021-04-01
| Invitation Email Blast | 6 | 2021-04-08
| Work with Development Officers to distribute to donors | 6
| Notify Insitution Staff of Event | 6 | 2021-04-08
| Invitation Reminder/Follow-up As needed | 2 | 2021-05-06
Event materials
Determine Event Materials Required |  | 4 | 2021-04-22
Custom materials
| Posters Signage to print | 3 | 2021-04-29
| Draft Agenda/Program | 3 | 2021-04-29
| Agenda/program to print | 2 | 2021-05-06
| Draft evaluation form | 2 | 2021-05-06
| Name Tags to Print | 1 | 2021-05-13
| Tent cards with speakers names to print | 1 | 2021-05-13
| Print/Gather handouts/brochures/reports | 1 | 2021-05-13
| Print Evaluation Form | 1 | 2021-05-13
General Supplies
| Sign for podium | 2 | 2021-05-06
| Signs for lobby | 2 | 2021-05-06
| Easels | 2 | 2021-05-06
| Flipcharts,Markers | 1 | 2021-05-13
| Media sign-in Form | 1 | 2021-05-13
| Registration/sign in sheets (include eNewsletter sign up) | 1 | 2021-05-13
| Basket to collect evaluations | 1 | 2021-05-13
| Pencils/Pens for Sign-in and Evaluation Cards, Question Cards | 1 | 2021-05-13
| Tape | 1 | 2021-05-13
| Your business cards | 1 | 2021-05-13
| Giveaway items | 3 | 2021-04-29
| Blank question cards | 1 | 2021-05-13
| Water for panelists | 0 | 2021-05-20
Food and Beverage
Order food and beverage |  | 4 | 2021-04-22
Confirm Food and Beverage based on rgistered attendee numbers |  | 1 | 2021-05-13
Manage event day food logistics |  | 0 | 2021-05-20
Audio Visual
Determine AV requirements – screen, projector, slides, mics, multibox (for media) |  | 4 | 2021-04-22
Confirm AV set-up |  | 1 | 2021-05-13
Volunteers/Staff
Determine volunteers needed and make request |  | 4 | 2021-04-22
Attendee Sign-in / Name Badges
AV/Signage coodination
Evaluations and handouts
Food and Beverage
Media sign-in
Questions
Ushers/Greeters
Confirm volunteer slots and provide instructions |  | 2 | 2021-05-06
Press Materials
Early pitch for long lead-time media, such as TV |  | 6 | 2021-04-08
Speaker and UWBA bios |  | 3 | 2021-04-29
List of spokespeople (CBOs, county officials) available for interviews |  | 3 | 2021-04-29
Media Alert/Invitation Drafted |  | 2 | 2021-05-06
Q&A developed |  | 3 | 2021-04-29
Press Release Drafted |  | 3 | 2021-04-29
Fact sheets |  | 2 | 2021-05-06
Final Press Release/Media Alert Approved |  | 1 | 2021-05-13
Assemble press kits |  | 0 | 2021-05-20
Post Press Materials on Web |  | 0 | 2021-05-20
PSA |  | TBD
Print Advertising |  | TBD
Op-ed |  | TBD
Post-Event
Thank yous |  | 0 | 2021-05-20
Evaluations |  | 1 | 2021-05-27
Communicate event success/share media clips with donors |  | 1 | 2021-05-27
Story in eNewsletter and/or blog post |  | TBD
Debriefing session with UWBA staff team |  | 1 | 2021-05-27
Solicit feedback from UWBA staff that attended event |  | 0 | 2021-05-20
Debriefing with panelists |  | 0 | 2021-05-20
Debriefing session with partners/vendors |  | 2 | 2021-06-03
Book speaking engagements/Consider duplicating event at other venues |  | TBD
Brief Development Officers and arrange campaign visits |  | 2 | 2021-06-03
Post online answers to unanswered questions from event |  | 2 | 2021-06-03
Determine if correct number of reports were printed (3 mos. Out) |  | 12 | 2021-08-12
Revisit strategy/tactics for getting press coverage in 3 mos, 6 mos. |  | 6 | 2021-07-01
Formulas:
Target Date = Event-([Weeks Out]*7)
Target Date = Event+([Weeks Out]*7)

## Virtual Event
Fill in your event name and date in the yellow boxes below and dates for each task will automatically update. This list provides suggested timing -- please modify the tasks and timeline to meet the requirements of your specific event.
Virtual Event Name |  | Virtual Event Date: | 2021-05-20
|  | Weeks Out | Target Date | Status
Venue/Budget
Draft virtual event budget, objectives, attendence goals; format and panelist options |  | 20 | 2020-12-31
Research virtual platforms, and date options |  | 18 | 2021-01-14
Book virtual event platform/Confirm virtual event format and date |  | 16 | 2021-01-28
Schedule a meeting with the Marketing Lead at the Community College to go over logistics, dates, times, details, etc.
Work with Development Officers to identify donors that might want to sponsor/participate in virtual event |  | 12
Determine Breakout Room-Set Up (if any)/Group test of platform |  | 3 | 2021-04-29
Confirm technical support needs (if any) with virtual platform vendor |  | 1 | 2021-05-13
Speakers/Panel
Recruit panelists |  | 12 | 2021-02-25
Finalize/confirm all panelists |  | 8 | 2021-03-25
Collect bios |  | 6 | 2021-04-08
Create script/slides for UWBA speakers |  | 3 | 2021-04-29
Draft script for speakers and/or panel questions |  | 3 | 2021-04-29
Recruit CBOs, clients and county officials to act as media spokespersons |  | 3 | 2021-04-29
Provide or collect script/anticipated questions |  | 2 | 2021-05-06
Final instructions to all speakers/panelists |  | 1 | 2021-05-13
Invitation
Determine invitation format (electronic/printed) and requirements |  | 12 | 2021-02-25
Print Invitation
| Invitation design approved (allow 2 weeks for printing, 1 week for prep) | 9 | 2021-03-18
| Compile mailing lists (print and electronic) | 9 | 2021-03-18
| Invitations printed | 7 | 2021-04-01
| Prep Invitation mailing | 7 | 2021-04-01
| Invitations in the Mail | 6 | 2021-04-08
Electronic Invitation
| Email list compiled | 9 | 2021-03-18
| Draft invitation designed | 8 | 2021-03-25
| Final invitation approved | 7 | 2021-04-01
| Invitation Email Blast | 6 | 2021-04-08
| Work with Development Officers to distribute to donors | 6
| Notify Insitution Staff of virtual event | 6 | 2021-04-08
| Invitation Reminder/Follow-up As needed | 2 | 2021-05-06
Virtual Event materials
Determine Virtual Event Materials Required |  | 4 | 2021-04-22
Custom materials
| Draft Agenda/Program | 3 | 2021-04-29
| Final agenda/program | 2 | 2021-05-06
| Draft evaluation form | 2 | 2021-05-06
| Gather handouts/brochures/reports | 1 | 2021-05-13
| Final Evaluation Form | 1 | 2021-05-13
Audio Visual
Determine AV requirements – extra monitors, mics, webcams, etc. |  | 4 | 2021-04-22
Confirm AV set-up |  | 1 | 2021-05-13
Volunteers/Staff
Determine volunteers needed and make request |  | 4 | 2021-04-22
Manage waiting room
AV coodination
Evaluations and handouts
Questions
Confirm volunteer slots and provide instructions |  | 2 | 2021-05-06
Press Materials
Early pitch for long lead-time media, such as TV |  | 6 | 2021-04-08
Speaker and UWBA bios |  | 3 | 2021-04-29
Media Alert/Invitation Drafted |  | 2 | 2021-05-06
Q&A developed |  | 3 | 2021-04-29
Press Release Drafted |  | 3 | 2021-04-29
Fact sheets |  | 2 | 2021-05-06
Final Press Release/Media Alert Approved |  | 1 | 2021-05-13
Assemble digital press kits |  | 0 | 2021-05-20
Post Press Materials on Web |  | 0 | 2021-05-20
PSA |  | TBD
Print Advertising |  | TBD
Op-ed |  | TBD
Post-Event
Thank yous |  | 0 | 2021-05-20
Evaluations |  | 1 | 2021-05-27
Communicate event success/share media clips with donors |  | 1 | 2021-05-27
Story in eNewsletter and/or blog post |  | TBD
Debriefing session with UWBA staff team |  | 1 | 2021-05-27
Solicit feedback from UWBA staff that attended event |  | 0 | 2021-05-20
Debriefing with panelists |  | 0 | 2021-05-20
Debriefing session with partners/vendors |  | 2 | 2021-06-03
Book speaking engagements/Consider duplicating event for other programs |  | TBD
Brief Development Officers and arrange campaign visits |  | 2 | 2021-06-03
Post online answers to unanswered questions from event |  | 2 | 2021-06-03
Revisit strategy/tactics for getting press coverage in 3 mos, 6 mos. |  | 6 | 2021-07-01
Formulas:
Target Date = Event-([Weeks Out]*7)
Target Date = Event+([Weeks Out]*7)